## Implementation Plan
Phase | Milestone | Task / Deliverable | Est. Days | Status | Priority | Dependencies | Completion % | Notes
0 | Room Maker | Finish and test Room Maker: draw, save, reopen, edit, validate JSON | 2 | Done | High | - | 100% | Create at least 3 test room templates
1 | Room Foundation | Design and implement BoardCell + CellType representation | 2 | Done | High | Phase 0 | 0% | GROUND / WALL / GAP / ENTRANCE / DOOR
1 | Room Foundation | Update Board to own/query the room grid | 2 | Done | High | BoardCell | 0% | Board handles physical terrain queries
2 | Room Loading | Implement Room / RoomTemplate JSON loading | 3 | Done | High | Phase 1 | 0% | Read sparse layered JSON
2 | Room Loading | Resolve higher-layer terrain overwrite and generic object markers | 1 | Done | High | JSON loader | 0% | Different categories may coexist
3 | Room Transition | Derive entrance/door direction from boundary position | 1 | Done | High | Phase 2 | 0% | No stored direction metadata
3 | Room Transition | Spawn snake inward from entrance with correct direction | 1 | Done | High | Entrance loading | 0% | No explicit spawn marker
3 | Room Transition | Choose compatible next room and integrate existing stage-change flow | 2 | Not Started | High | Door direction | 0% | Exit RIGHT -> next LEFT entrance, etc.
4 | Terrain Playtest | Implement/test wall, ground, gap, entrance and door behavior | 2 | Not Started | High | Phase 3 | 0% | Gap is instant death; entrance behaves like wall
4 | Terrain Playtest | Playtest full-floor, gap and one-tile bridge room templates | 1 | Not Started | High | Terrain behavior | 0% | Verify room traversal before combat
5 | Snake Damage | Add per-body-node HP | 2 | Not Started | High | Rooms stable | 0% | Default/easy 3 HP; difficulty may reduce later
5 | Snake Damage | Implement explicit attack damage to body nodes | 1 | Not Started | High | Node HP | 0% | Ordinary collision causes no combat damage
5 | Snake Damage | Cut destroyed node and all nodes behind it | 1 | Not Started | High | Node damage | 0% | Reuse/adapt existing TailCut logic
5 | Snake Damage | Implement minimum survival length = 3 | 1 | Not Started | High | Tail cut | 0% | Damaging hit at length 3 kills player
6 | Food | Repair damaged nodes nearest-to-head before growth | 1 | Not Started | Medium | Phase 5 | 0% | Default food fully repairs one damaged node
6 | Food | Grow snake only when no damaged nodes remain | 1 | Not Started | Medium | Food repair | 0% | Playtest repair/growth loop
7 | Combat Foundation | Design generic attack representation / hit region | 2 | Not Started | High | Snake damage | 0% | Architecture review before implementation
7 | Combat Foundation | Implement player Attack button + one weapon | 2 | Not Started | High | Attack representation | 0% | Snake keeps moving during attack
7 | Combat Foundation | Implement Spell button / generic spell hook | 2 | Not Started | Medium | Attack representation | 0% | Foundation only; one simple spell is enough
8 | Enemy Foundation | Implement one basic enemy using grid/top-down movement | 2 | Not Started | High | Combat foundation | 0% | Start with one simple enemy
8 | Enemy Foundation | Implement explicit enemy attack region against snake nodes | 2 | Not Started | High | Basic enemy | 0% | No contact damage
8 | Enemy Foundation | Playtest player ↔ enemy combat in rooms | 1 | Not Started | High | Enemy attack | 0% | Validate both damage directions
9 | Wrap Attack V1 | Track snake cell occupancy including overlapping nodes | 1 | Not Started | High | Movement stable | 0% | Occupancy should be count-based
9 | Wrap Attack V1 | Flood-fill exterior and determine enclosed cells | 2 | Not Started | High | Occupancy | 0% | Snake cells act as blocked walls
9 | Wrap Attack V1 | Compare enclosedBefore vs enclosedAfter for newly enclosed area | 1 | Not Started | High | Flood fill | 0% | Avoid repeated wrap damage
9 | Wrap Attack V1 | Validate full enemy footprint inside new wrap area | 1 | Not Started | High | New wrap area | 0% | Partial enclosure does not count
9 | Wrap Attack V1 | Apply one-time damage + stun and stress-test edge cases | 2 | Not Started | High | Wrap validation | 0% | Test coils, overlap, gaps, bridges, multiple regions
10 | Cypherrush Progression | Implement generic item/cipher collection foundation | 2 | Not Started | Medium | Combat stable | 0% | Cipher validation is order-independent
10 | Cypherrush Progression | Implement cipher inventory matching including duplicate letters | 1 | Not Started | Medium | Cipher items | 0% | Treat required letters/items as a multiset
10 | Cypherrush Progression | Implement Guardian Door / Boss Door gating foundation | 2 | Not Started | Medium | Cipher matching | 0% | Final boss door requires complete cipher
10 | Cypherrush Progression | Test basic run progression from rooms to cipher gate | 1 | Not Started | Medium | Door gating | 0% | No merchant/full story/final boss yet
11 | Integration | Full integration playtest | 2 | Not Started | High | Phases 0–10 | 0% | Run through complete foundation loop
11 | Integration | Refactor only issues exposed by implementation/playtesting | 2 | Not Started | Medium | Integration test | 0% | Avoid speculative architecture changes
11 | Integration | Lock first playable merged foundation milestone | 1 | Not Started | High | Integration stable | 0% | Ready for content expansion

## Dashboard
Rouge Snake × Cypherrush Implementation Tracker
Metric | Value | Phase | Milestone | Est. Days | Target
Total tasks | 34 | 0 | Room Maker | 2 | Tool JSON round-trip ready
Estimated development days | 53 | 1 | Room Foundation | 4 | BoardCell + Board ready
Completed tasks | 7 | 2 | Room Loading | 4 | JSON rooms load correctly
Overall completion | 2.941% | 3 | Room Transition | 4 | Room-to-room traversal
|  | 4 | Terrain Playtest | 3 | Stable room gameplay
|  | 5 | Snake Damage | 5 | Body-node HP/tail damage
|  | 6 | Food | 2 | Repair/growth loop
|  | 7 | Combat Foundation | 6 | Player weapon/spell foundation
|  | 8 | Enemy Foundation | 5 | Basic two-way combat
|  | 9 | Wrap Attack V1 | 7 | Flood-fill wrap playable
|  | 10 | Cypherrush Progression | 6 | Cipher/gating skeleton
|  | 11 | Integration | 5 | First merged playable milestone

## Design Decisions
Area | Locked Decision
Room files | One JSON format is used by both Room Maker and the C++ game.
Room generation | Use fixed validated room templates rather than arbitrary runtime geometry generation.
Layers | Editor JSON remains layered; Board represents only resolved permanent terrain.
Layer conflicts | Higher layer index overwrites lower layer for competing terrain at the same cell.
Coexistence | Different categories such as terrain + enemy/item/decoration may coexist at one grid position.
Brush identifiers | Use generic lowercase names such as ground, wall, gap, entrance, door, enemy, item.
Entrance/exits | Normal rooms have exactly 1 entrance and 1–3 one-cell exits on the boundary.
Spawn | Player spawn/direction is derived from entrance; no explicit spawn marker.
Gap | Entering a gap causes instant death.
Self collision | Snake may freely overlap/cross its own body; self-contact causes no damage.
Combat damage | Damage only comes from explicit attack regions/effects, not ordinary contact.
Body HP | Each snake body node has HP; default/easy baseline is 3 HP.
Tail damage | Destroyed node and everything behind it are cut off.
Minimum length | At length 3, another damaging hit kills the player.
Food | Food repairs damaged nodes nearest-to-head before growing the snake.
Wrap | Newly enclosed area is found using flood-fill; successful wrap deals one-time damage + stun.
Wrap enemy test | Enemy's complete occupied footprint must be inside the newly enclosed area.
Cipher | Cipher matching is order-independent and must handle duplicate required letters.
Development workflow | Discuss architecture → user implements C++ → review uploaded source → playtest → lock feature.